## Summary
Task Tracker — CASHPOS Phase 2
Feature: Product ¦ Diskon ¦ Promosi Platform: Dashboard ¦ BE ¦ Mobile
Feature | BE | Dashboard | Mobile | Total
Product | 11 | 7 | 6 | 24
Diskon | 8 | 5 | 5 | 18
Promosi | 9 | 6 | 4 | 19
TOTAL | 28 | 18 | 15 | 61
Platform Legend
BE
Dashboard
Mobile
Status Legend
TODO
IN PROGRESS
DONE
BLOCKED
REVIEW
Priority Legend
High
Medium
Low

## Tracker
No | Feature | Platform | Category | Task | Priority | Status | Assignee | Est. Days | Start Date | End Date | Notes
1 | Product | BE | CRUD | CRUD Produk SIMPLE (nama, harga, SKU, kategori, gambar) | High | TODO | Ray
2 | Product | BE | CRUD | CRUD Produk VARIANT — ProductVariantGroup + ProductVariant | High | TODO | Ray
3 | Product | BE | CRUD | CRUD Produk MODIFIER — ProductModifierGroup + ProductModifier | High | TODO | Ray
4 | Product | BE | CRUD | API upload & simpan gambar produk (Images) | Medium | TODO | Ray
5 | Product | BE | Business | Validasi perubahan productType (blokir revert jika ada transaksi) | High | TODO | Ray
6 | Product | BE | Business | Migrasi tipe: hapus variant/modifier saat ganti ke SIMPLE (safe delete) | Medium | TODO | Ray
7 | Product | BE | Stock | Tambah kolom variantId (nullable) ke tabel stock & StockMovement | High | TODO | Ray
8 | Product | BE | Stock | Validasi stock per variant saat transaksi (VARIANT product) | High | TODO | Ray
9 | Product | BE | Stock | Validasi stock di level produk saat transaksi (MODIFIER product) | Medium | TODO | Ray
10 | Product | BE | API | GET /products — list dengan filter kategori, tipe, isActive, search | High | TODO | Ray
11 | Product | BE | API | GET /products/{id} — detail + variant/modifier groups | High | TODO | Ray
12 | Product | Dashboard | UI | Halaman list produk — filter, search, tipe badge | High | TODO | Hafiz
13 | Product | Dashboard | UI | Form tambah/edit produk SIMPLE | High | TODO | Hafiz
14 | Product | Dashboard | UI | Form tambah/edit produk VARIANT — manajemen group & item variant | High | TODO | Hafiz
15 | Product | Dashboard | UI | Form tambah/edit produk MODIFIER — manajemen group & item modifier | High | TODO | Hafiz
16 | Product | Dashboard | UI | Upload foto produk dari form | Medium | TODO | Hafiz
17 | Product | Dashboard | UI | Konfirmasi & blokir perubahan tipe produk jika ada transaksi | Medium | TODO | Hafiz
18 | Product | Dashboard | UI | Manajemen stok per variant (input qty per variant item) | High | TODO | Hafiz
19 | Product | Mobile | Kasir | Tampil katalog produk di layar kasir (grid/list) | High | TODO | Gandha
20 | Product | Mobile | Kasir | Search produk by nama / SKU | High | TODO | Gandha
21 | Product | Mobile | Kasir | Pilih variant — modal pilihan variant group (wajib jika isRequired) | High | TODO | Gandha
22 | Product | Mobile | Kasir | Pilih modifier — modal pilihan modifier group (min/max select) | High | TODO | Gandha
23 | Product | Mobile | Kasir | Tampil harga modifier sebagai addon di cart item | Medium | TODO | Gandha
24 | Product | Mobile | Kasir | Blokir tambah item jika stok = 0 | High | TODO | Gandha
25 | Diskon | BE | CRUD | CRUD Diskon (nama, tipe, nilai, scope, kode, tanggal berlaku) | High | TODO | Ray
26 | Diskon | BE | Business | Validasi kode diskon — aktif, belum kadaluarsa, limit pemakaian | High | TODO | Ray
27 | Diskon | BE | Business | Hitung diskon scope ALL (dari total subtotal) | High | TODO | Ray
28 | Diskon | BE | Business | Hitung diskon scope PRODUCT (per item yang cocok productId) | High | TODO | Ray
29 | Diskon | BE | Business | Hitung diskon scope CATEGORY (per item yang masuk kategori) | High | TODO | Ray
30 | Diskon | BE | Business | Validasi maksimum 1 diskon per transaksi | High | TODO | Ray
31 | Diskon | BE | Business | Endpoint GET /discounts/active — list diskon codeless (tanpa kode) | Medium | TODO | Ray
32 | Diskon | BE | Business | Increment usageCount setelah transaksi PAID | Medium | TODO | Ray
33 | Diskon | Dashboard | UI | Halaman list diskon — status badge, tanggal berlaku | High | TODO | Hafiz
34 | Diskon | Dashboard | UI | Form tambah/edit diskon — tipe PERCENTAGE / NOMINAL | High | TODO | Hafiz
35 | Diskon | Dashboard | UI | Konfigurasi scope: ALL / PRODUCT (pilih produk) / CATEGORY (pilih kategori) | High | TODO | Hafiz
36 | Diskon | Dashboard | UI | Toggle aktif/nonaktif diskon | Medium | TODO | Hafiz
37 | Diskon | Dashboard | UI | Tampilkan usage count & limit di list | Low | TODO | Hafiz
38 | Diskon | Mobile | Kasir | Input kode diskon di halaman cart/payment | High | TODO | Gandha
39 | Diskon | Mobile | Kasir | Pilih diskon dari list (codeless) — sheet bottom dengan list aktif | High | TODO | Gandha
40 | Diskon | Mobile | Kasir | Tampil potongan diskon per item dan total di cart | High | TODO | Gandha
41 | Diskon | Mobile | Kasir | Hapus / ganti diskon yang sudah dipilih | Medium | TODO | Gandha
42 | Diskon | Mobile | Kasir | Pesan error jika kode tidak valid / expired / limit habis | Medium | TODO | Gandha
43 | Promosi | BE | CRUD | CRUD Promosi (nama, tipe, kondisi, tanggal, priority, canCombine) | High | TODO | Ray
44 | Promosi | BE | Business | Auto-apply tipe DISCOUNT_BY_ORDER — diskon dari subtotal order | High | TODO | Ray
45 | Promosi | BE | Business | Auto-apply tipe BUY_X_GET_Y — deteksi item qualifying & gratis | High | TODO | Ray
46 | Promosi | BE | Business | BUY_X_GET_Y: isMultiplied — kalikan reward jika qty > threshold | Medium | TODO | Ray
47 | Promosi | BE | Business | Auto-apply tipe DISCOUNT_BY_ITEM_SUBTOTAL — diskon per item jika subtotal item >= N | High | TODO | Ray
48 | Promosi | BE | Business | Logika priority — urutkan promosi, terapkan tertinggi dulu | High | TODO | Ray
49 | Promosi | BE | Business | Logika canCombine — terapkan semua jika true, berhenti di canCombine=false tertinggi | High | TODO | Ray
50 | Promosi | BE | Business | Filter promosi per outlet (outletId) saat kalkulasi | Medium | TODO | Ray
51 | Promosi | BE | API | GET /promotions/applicable — list promosi yang akan diterapkan untuk cart | Medium | TODO | Ray
52 | Promosi | Dashboard | UI | Halaman list promosi — tipe badge, status aktif, priority | High | TODO | Hafiz
53 | Promosi | Dashboard | UI | Form tambah/edit promosi — tipe DISCOUNT_BY_ORDER | High | TODO | Hafiz
54 | Promosi | Dashboard | UI | Form tambah/edit promosi — tipe BUY_X_GET_Y (pilih item X, item Y gratis) | High | TODO | Hafiz
55 | Promosi | Dashboard | UI | Form tambah/edit promosi — tipe DISCOUNT_BY_ITEM_SUBTOTAL | High | TODO | Hafiz
56 | Promosi | Dashboard | UI | Konfigurasi priority & canCombine | Medium | TODO | Hafiz
57 | Promosi | Dashboard | UI | Assign promosi ke outlet tertentu | Medium | TODO | Hafiz
58 | Promosi | Mobile | Kasir | Tampil badge/label promosi yang aktif diterapkan di cart | High | TODO | Gandha
59 | Promosi | Mobile | Kasir | Tampil item gratis hasil BUY_X_GET_Y di cart (harga Rp 0) | High | TODO | Gandha
60 | Promosi | Mobile | Kasir | Rincian potongan promosi di halaman payment summary | High | TODO | Gandha
61 | Promosi | Mobile | Kasir | Informasi promo aktif hari ini di halaman kasir (banner / chip) | Low | TODO | Gandha
62 | Settlement | Dashboard | UI | Tampilan field FEE pada settlement disesuaikan sesuai role | High | TODO | Hafiz | 1 | 2026-04-08 | 2026-04-08